## Daily Plan
Week | Date | Day | Phase | Planned Hrs | Topic | Task / Deliverable | Exam Domain | Status | Actual Hrs
1 | 2026-10-13 | Tue | 1 Core services | 1 | Orientation | Read SAA-C03 exam guide + domain weights. Set up AWS free-tier account, billing alarm, MFA. | All | Not started
1 | 2026-10-14 | Wed | 1 Core services | 1 | IAM | Users, groups, roles, policies (identity vs resource-based). | Secure | Not started
1 | 2026-10-15 | Thu | 1 Core services | 1 | IAM / Organizations | STS, SCPs, permission boundaries, cross-account access. | Secure | Not started
1 | 2026-10-16 | Fri | 1 Core services | 1 | S3 basics | Storage classes, versioning, lifecycle rules, static hosting. | Cost / Resilient | Not started
1 | 2026-10-17 | Sat | 1 Core services | 1.5 | S3 security + LAB | Bucket policies, encryption, replication. LAB: bucket + lifecycle + policy. | Secure | Not started
1 | 2026-10-18 | Sun | 1 Core services | 1.5 | EC2 | Instance families, purchasing options (On-Demand/Reserved/Spot), AMIs, placement groups. | Performance / Cost | Not started
1 | 2026-10-19 | Mon | 1 Core services | 1 | EBS / EFS / FSx | Volume types, snapshots, instance store, EFS vs FSx use cases. | Performance | Not started
2 | 2026-10-20 | Tue | 1 Core services | 1 | VPC (1) | Subnets, route tables, IGW, NAT gateway. (Map to what you know from Network+.) | Secure / Resilient | Not started
2 | 2026-10-21 | Wed | 1 Core services | 1 | VPC (2) | Security groups vs NACLs, VPC endpoints, peering, Transit Gateway, VPN/Direct Connect. | Secure | Not started
2 | 2026-10-22 | Thu | 1 Core services | 1 | Route 53 | Routing policies (failover, latency, weighted, geo), health checks. | Resilient | Not started
2 | 2026-10-23 | Fri | 1 Core services | 1 | ELB + Auto Scaling | ALB vs NLB vs GWLB, scaling policies, health checks. | Resilient / Performance | Not started
2 | 2026-10-24 | Sat | 1 Core services | 1.5 | LAB: VPC + ALB + ASG | Build custom VPC, launch EC2 behind ALB with ASG. Tear down after. | Resilient | Not started
2 | 2026-10-25 | Sun | 1 Core services | 1.5 | Review + questions | Re-read weak notes. 20 practice questions on IAM/S3/EC2/VPC. Log wrong answers. | All | Not started
2 | 2026-10-26 | Mon | 2 Data, decoupling, security | 1 | RDS & Aurora | Multi-AZ vs read replicas, Aurora features, backups, RDS Proxy. | Resilient | Not started
3 | 2026-10-27 | Tue | 2 Data, decoupling, security | 1 | DynamoDB | Capacity modes, DAX, global tables, streams. | Performance | Not started
3 | 2026-10-28 | Wed | 2 Data, decoupling, security | 1 | Other data services | ElastiCache, Redshift, Athena, Glue, EMR. Learn the 'which DB for which scenario' map. | Performance | Not started
3 | 2026-10-29 | Thu | 2 Data, decoupling, security | 1 | SQS / SNS | Standard vs FIFO, DLQ, fan-out pattern. | Resilient | Not started
3 | 2026-10-30 | Fri | 2 Data, decoupling, security | 1 | EventBridge / Kinesis / Step Functions | When to use each; decoupling patterns. | Resilient | Not started
3 | 2026-10-31 | Sat | 2 Data, decoupling, security | 1.5 | Lambda + API Gateway + LAB | Concurrency, triggers, limits. LAB: Lambda + API Gateway + DynamoDB. | Performance | Not started
3 | 2026-11-01 | Sun | 2 Data, decoupling, security | 1.5 | Review + questions | 25 practice questions on databases + decoupling. Log wrong answers. | All | Not started
3 | 2026-11-02 | Mon | 2 Data, decoupling, security | 1 | CloudFront / Global Accelerator | Caching, OAC, edge use cases, GA vs CloudFront. | Performance | Not started
4 | 2026-11-03 | Tue | 2 Data, decoupling, security | 1 | Encryption | KMS, Secrets Manager, ACM, CloudHSM, encryption at rest/in transit. | Secure | Not started
4 | 2026-11-04 | Wed | 2 Data, decoupling, security | 1 | Threat protection | WAF, Shield, GuardDuty, Inspector, Macie, Firewall Manager. | Secure | Not started
4 | 2026-11-05 | Thu | 2 Data, decoupling, security | 1 | Monitoring / governance | CloudWatch, CloudTrail, Config, Systems Manager, Trusted Advisor. | Secure / Cost | Not started
4 | 2026-11-06 | Fri | 2 Data, decoupling, security | 1 | Cost optimization | Savings Plans, Reserved, Spot, Cost Explorer, Budgets, S3 tiering. | Cost | Not started
4 | 2026-11-07 | Sat | 2 Data, decoupling, security | 1.5 | Migration + DR | DMS, Snow family, DataSync, Storage Gateway, AWS Backup, DR strategies (RTO/RPO). | Resilient | Not started
4 | 2026-11-08 | Sun | 3 Practice & weak spots | 2 | PRACTICE EXAM #1 | Full timed practice exam (65 Qs). Do NOT skip. Record score on 'Practice Exams' tab. | All | Not started
4 | 2026-11-09 | Mon | 3 Practice & weak spots | 1 | Review exam #1 | Go through every wrong AND guessed question. Write the reason in your own words. | All | Not started
5 | 2026-11-10 | Tue | 3 Practice & weak spots | 1 | Weak area #1 | Re-study the lowest-scoring domain from exam #1. | Per exam #1 | Not started
5 | 2026-11-11 | Wed | 3 Practice & weak spots | 1 | Weak area #2 | Re-study second-lowest domain. 20 targeted questions. | Per exam #1 | Not started
5 | 2026-11-12 | Thu | 3 Practice & weak spots | 1 | Resilient architectures | Multi-AZ/multi-region patterns, failover, backup, RTO/RPO scenarios. | Resilient | Not started
5 | 2026-11-13 | Fri | 3 Practice & weak spots | 1 | Performance + cost scenarios | Pick-the-right-service scenario questions. Compare similar services side by side. | Performance / Cost | Not started
5 | 2026-11-14 | Sat | 3 Practice & weak spots | 2 | PRACTICE EXAM #2 | Full timed practice exam. Target 75%+. Record score. | All | Not started
5 | 2026-11-15 | Sun | 3 Practice & weak spots | 1.5 | Review exam #2 | Review every wrong/guessed question. Update cheat sheet. | All | Not started
5 | 2026-11-16 | Mon | 4 Final review | 1 | Weak-area drill | Drill remaining weak topics only. No new material from here on. | Per exam #2 | Not started
6 | 2026-11-17 | Tue | 4 Final review | 1 | Timed question set | 30 mixed questions in 45 min. Record score on 'Practice Exams' tab. | All | Not started
6 | 2026-11-18 | Wed | 4 Final review | 1 | Service comparison sheet | One-page comparison (SQS vs SNS, EBS vs EFS, NLB vs ALB, etc). | All | Not started
6 | 2026-11-19 | Thu | 4 Final review | 1 | Light review | Skim notes + cheat sheet. Confirm exam booking, ID, test-center/online setup. | All | Not started
6 | 2026-11-20 | Fri | 4 Final review | 0.5 | Rest | 30-minute skim only. Sleep early. No cramming. | All | Not started
6 | 2026-11-21 | Sat | 4 Final review | 0 | EXAM DAY | Take the AWS SAA-C03 exam. | All | Not started
|  |  |  | 44.5 | TOTAL |  |  |  | 0

## Weekly Summary
Week | Starts | Planned Hrs | Actual Hrs | Days Done | Days Planned | Completion % | Behind?
1 | 2026-10-13 | 8 | 0 | 0 | 7 | 0% | -
2 | 2026-10-20 | 8 | 0 | 0 | 7 | 0% | -
3 | 2026-10-27 | 8 | 0 | 0 | 7 | 0% | -
4 | 2026-11-03 | 8.5 | 0 | 0 | 7 | 0% | -
5 | 2026-11-10 | 8.5 | 0 | 0 | 7 | 0% | -
6 | 2026-11-17 | 3.5 | 0 | 0 | 5 | 0% | -
TOTAL |  | 44.5 | 0 | 0 | 40 | 0%
Days until exam: |  | 39
Domain weights (SAA-C03): Secure 30% ¦ Resilient 26% ¦ High-performing 24% ¦ Cost-optimized 20%
Formulas:
Starts = DATE(2026,10,13)+([Week]-1)*7
Behind? = IF(AND([Starts]+6<TODAY(),[Completion %]<1),"BEHIND",IF([Completion %]=1,"On track","-"))

## Practice Exams
Attempt | Date | Score % | Secure % | Resilient % | Performance % | Cost % | Weakest domain / notes
Exam #1 (diagnostic) | 2026-11-08
Exam #2 | 2026-11-14
Timed set (30 Qs) | 2026-11-17
Extra attempt
Target score before sitting the exam (hardcoded goal, edit if you like): |  |  |  |  | 80%
Ready? |  |  |  |  | No data
Legend: blue = cells for you to fill in. Official pass mark is 720/1000, but practice exams run easier or harder, so aim well above it.

## Read Me
HOW THIS PLAN WAS BUILT
Exam: AWS Solutions Architect Associate (SAA-C03), 21 Nov 2026. Plan starts 13 Oct 2026.
Inputs you gave: ~1 hr per weeknight, 1-2 hrs per weekend day (planned at 1.5 hrs; 2 hrs on practice-exam days), working Mon-Fri, weekend part-time class.
Resource: AWS SAA partner readiness modules (no hands-on labs included) -> short labs added on weekends (marked LAB).
Assumption: you already hold CCP and Network+, so cloud basics and networking get less time than a beginner would need.
RULES
1. Update Status and Actual Hrs daily. The 'Weekly Summary' tab shows if you are behind.
2. Total planned hours are the minimum, with almost no slack. Missing 3-4 days puts the date at risk; make up lost hours on the weekend, do not drop practice exams.
3. Practice exams: you need your own question bank (AWS official practice questions or a third-party set). The modules alone are not enough.
4. From 16 Nov: no new material. Only review and weak areas.
5. Tear down every lab resource after use to avoid AWS charges.